## Slide 1: Planning a training course Steps, resources and logistics
Training of Trainers in Epidemiology of Vaccine Preventable Diseases
Created in February 2012, Revised May 2018
Notes: Facilitator notes:

## Slide 2: Objectives
Specific objectives of this session:
List the steps in the planning of a training course;
Define the principles of training course evaluation;
Identify the logistical aspects (including budgetary) in the training course planning.
Related to the course objectives:
A. Mobilise resources (human, budget, etc) to organise training in this area.
Notes: Facilitator notes:

## Slide 3: Outline
This session consists of the following elements
The training framework
Importance of careful planning
Evaluation of training activities
Participant expectations
Notes: Facilitator notes:

## Slide 4: The training framework

## Slide 5
Training needs assessment
Learning objectives
Curriculum
Evaluation
Quality
Delivery
planning
Training Framework
Notes: 5

## Slide 6: Importance of careful planning

## Slide 9: Planning – steps (4 months before...)
Identify coordinator(s) of the event
Identify budget
Describe in draft the activity (topic, background, target, learning objectives, methods, draft agenda)
Explore potential facilitators for pedagogical team
Identify venue and dates
Book rooms for the training event
Assess needs of equipment and materials in the class-room
Confirm the interest and availability of facilitators
Finalise learning objectives and curriculum
Ask offers for catering/accommodation/ transport
Prepare budget request
Notes: Facilitator notes:

## Slide 10: Planning – steps (3 months before...)
Inform counterparts, stakeholders
  ECDC Competent Bodies
  Disease specific networks
  Epiet Training Site Forum
Publish information about the event online
Select participants
Submit information to EACCME for accreditation
Notes: Facilitator notes:

## Slide 11: Planning – steps (2 months before...)
Collect all e-mails and self-assessment questionnaires
Create a list with the names of participants
Inform participants & send agenda
Send documents for travel and reimbursement rules
Send documents to Missions & Meetings
Review agenda and training materials with pedagogical team
Notes: Facilitator notes:

## Slide 12: Planning – steps (1 month before...)
Send calendar invitation to facilitators with final agenda
Send the order to the company that provide catering
Request wifi connection
Excel sheet of participants for control of attendance
Create new user accounts for Extranet and inform the users
Design evaluation forms together with facilitators
Reminders about lesson plans and training materials
Notes: Facilitator notes:

## Slide 13: Planning – steps (1 week before...)
Order materials to Facility management (colour marker, post-it, pens, handouts..)
Propose layout of the room and equipment necessary (flip-charts, projector, computer, remote, laser pointer)
Create an Attendance List to be shared with participants
Prepare badges and name plates
Upload presentations and documents in USB stick or plan access to EXTRANET
Print handouts
Create certificates of attendance
Reminders to facilitators and participants if needed
Notes: Facilitator notes:

## Slide 14: Planning – steps (1 day before...)
Double check facility, layout of the rooms and equipment
Another look to the checklist
Breathe...and extinguish any fire...
Notes: Facilitator notes:

## Slide 15: Delivery
Information, code of conduct
Collect expectations from participants
Monitor needs of facilitators
Continuous evaluation

## Slide 16: (...After)
Analyse evaluation forms and write evaluation report
Send evaluation report to accreditation system
Registration of participants in our database
Comments

## Slide 17: Evaluation of training activities

## Slide 18
Training needs assessment
Learning objectives
Curriculum
Evaluation
Quality
Delivery
planning
Training framework
Notes: 18

## Slide 19: Purpose of evaluation
To check if:
The goals have been achieved
The learning objectives have been fulfilled
Resources have been efficiently used
Students and teachers were satisfied
And additionally:
To improve next training activity
To help identify training needs
Notes: Facilitator notes:

## Slide 20: The four levels of evaluation
1 Reaction Immediate reaction of trainees
2 Learning Increase in trainees’ knowledge and skills
3 Behaviour How trainees apply their new knowledge and skills
4 Results How the training affects the trainees’ broader area of work
Notes: Facilitator notes:

## Slide 21: Evaluation of satisfaction – level 1
Feedback forms
Scoring:
Likert scale: Agreement with statements (e.g. The activity fulfilled my expectations): 1=strong disagreement; 2= disagreement; 3= neutral; 4= agreement; 5= strong agreement
Qualifiers for content (poor, adequate, fair, good, very good)
Qualifiers for level (too basic, appropriate, too advanced)
Open questions
What did you like most?
What needs improvement?
Additional comments
Interview – individual or group feedback: the facilitator poses open questions and writes the answers on a flip-chart, confirming agreement; use list of expectations
Advantages: open discussion, possibility of clarifying specific points
Disadvantages: not anonymous, possible deviation of the scope of the evaluation
Notes: Facilitator notes:

## Slide 22: Evaluation at level 2 - learning
Verbal questions during the training
Role play
Work-related exercises
Written or oral tests at the end of the training
“Before and after” exercises
Notes: Facilitator notes:

## Slide 23: Evaluation at level 3- application knowledge and skills
Surveys and questionnaires
Follow-up interviews and training sessions
Focus groups
Work assignments based on the training
Action plans
On-the-job observation by independent observer
Notes: Facilitator notes:

## Slide 24: Evaluation methods at level 4 - results
Public health programme performance monitoring
  Questionnaires at public health programme level
  Action plans
Focus groups
Simulation exercises
Notes: Facilitator notes:

## Slide 25: Participant expectations

## Slide 26: Main theme: Looking for answers to vaccinology problems
KNOWLEDGE
More ideas
Share experiences
More competence
Set of knowledge ready-to-use for post graduate training
Effective interventions
RELATIONSHIPS
Networking opportunity
Notes: Facilitator notes:

## Slide 27: Main theme: Looking for answers to vaccinology problems
COMMUNICATION
manage resistance of groups of people and health professionals
how best communicate with different people
ideas to motivate and promote vaccination in difficult groups
health professionals that are expected to vaccinate themselves
health professionals that are expected to communicate about vaccination and to vaccinate the general public
parents and other activists against vaccination
migrants (irregulars, language and cultural barriers)
Notes: Facilitator notes:

## Slide 28: Main theme: Looking for answers to vaccinology problems
TRAINING METHODS
more ideas and tools
new approaches to teaching
improve teaching
material for courses
ways to disseminate the course
Notes: Facilitator notes:

## Slide 29: References
Guide for Evaluating training in WHO: http://www.who.int/influenza/evaluating_training/en/index.html
Milagros García-Barbero Alfonso Roca, María Teresa Martínez Moratalla, María Consuelo. How to develop educational programmes for health professionals. Escuela Andaluza de Salud Publica, Granada, 1998.
Notes: Facilitator notes:

## Slide 30: Acknowledgements This training material was created by ECDC with the direct involvement of Carmen Varela Santos, Liliya Todorova-Janssens, Laura Campagnoli, and reference to Anouk Berger, WHO The revision and update of this training material was commissioned in 2017 by ECDC to Transmissible with the direct involvement of Pawel Stefanoff and Arnold Bosman
Notes: Facilitator notes: